## WorkPlan
RACI Matrix
Sr. No | Phases and Activities | Responsible | Accountable | Consulted | Informed | Target Start Date | Target End Date | No of Days | Revised End Dates | Completion Date | RAG | Remarks
1 | DISCOVERY
1.1 | Identify stakeholders
1.2 | Identify vision, mission, goals
1.3 | Setup of Data Strategy Workshops
1.4 | Agree Governance charter
1.5 | Develop Governance Framework and Standards
1.6 | Identify and document Data Landscape
1.7 | Agree on Pillars of Data Maturity Model, governance Framework, Standards, policies and Procedures
1.8 | Setup Data Governance Forums and Working Groups
1.9 | Agree on Data standards, policies, and procedures
2 | BASELINE
2.1 | Assess data governance maturity level
2.2 | Establish data governance target maturity level
2.3 | Review data architecture
2.4 | Define Data stewardship
2.5 | Agree on Data standards, policies, and procedures
2.6 | Build Document Repository
2.4 | Data Dictionaries with Data Privacy Classification
3 | TARGET
3.1 | Agree on Data standards, policies, and procedures for Future
3.2 | Define organizational structure and roles
3.3 | Define governance process
3.4 | Identify required tools
3.5 | Agree on Target State
4 | PLAN / ROADMAP
4.1 | Gap analysis
4.2 | Identify / prioritize activities
4.3 | Develop data management roadmap
5 | EXECUTION
5.1 | Fill roles
5.2 | Develop policies
5.3 | Communicate with stakeholders
5.4 | Measure performance and monitor feedback
6 | LAUNCH
Formulas:
No of Days = IF(OR([Target Start Date]="",[Target End Date]=""),"",NETWORKDAYS([Target Start Date],[Target End Date])& " day(s)")

## Pre-Requisites for Client
Category | Question | Status
Kick-off | Are Source System Technology teams have been Engaged?
Is Client’s local IT and external 3rd parties contact aware of the project?
Do we have named resources from Client’s Local IT and Application Support team?
Do we have signed off business requirements?
Is Roles and Responsibilities agreed?
Data Readiness | Has Data Sources Fully Identified?
Has SLA agreed with source teams?
Is expectation matrix defined for breach of SLAs?
Has all KPIs ben identified and captured?
Source To Target Done?
Data Glossary Created?
Historic Data Captured?
Data Load Schedule Captured?
IT Readiness | Is Infra Access Granted to Vendor team?
Has Security roles and permission and policies in-place for project infra setup?
Who in the Local IT team will assist with setting up of VPC paring for data pull?
Any guidelines on connectivity standards with Developer Laptops?
IS DEV, TEST and Production environment required and ready?
Process to enable Vendor Data access on Client environment finalized?
Data Acquisition & Validation | Provide list of ETL Pipelines
Data lake design and Data Warehouse
Create DQ Rules
Data Validation
Known Data Issues
Build & Deploy | Logical and Physical model
Dev/Test Deployment Process
Data Validation Routines
Production Deployment Process
UAT/Approval | User Testing Process
Bug Identification and Tracking
Bug Fixing Process
UAT Sign-off & Go Live