## WorkPlan
|  | RACI Matrix | [10 empty] | Delayed
Sr. No | Phases and Activities | Responsible | Accountable | Consulted | Informed | Target Start Date | Target End Date | No of Days | Revised End Dates | Completion Date | RAG | Remarks | Needs Urgent Attention
1 | Sprint 0 - Discovery Phase | [11 empty] | In Progress
1.1 | Agree on Scope and Roles and Responsibilities | [11 empty] | Completed
1.2 | Signed of FRD
1.3 | Security Profiling Rules for Mapping
1.4 | Identify Source System
1.5 | Create Bus Matrix basis the FRD
1.6 | Test Source System Connectivity
1.7 | Complete Source To Target Mapping
1.8 | Provide Data Load Schedule and Time - (time data available in source system)
1.9 | Sign of Souce to Target Mapping
1.1 | Sign of Bus Matrix
2 | Sprint 1 - Data Acquisition & Validation
2.1 | Acquire Historic Load
2.2 | Build ETL Pipelines
2.3 | Create DQ Rules
2.4 | Update Data Glossary in Scikiq
2.5 | Test Data Load
2.6 | Resolve Data Issues
2.7 | Show and Tell Data Analysis
2.8 | Data Quality Sign Off
3 | Sprint 2 Phase 1 KPIs / Screens - Build & Deploy
3.1 | Data Modelling
a | Selection of Attributes, Columns & Matrix
b | Establish relationship between tables
c | Create Reporting Tables
3.2 | Reporting Build
a | Creation of Data Models in Reporting & Establish Relationships
b | Creation of Calculation & Major Matrix
c | Build Wireframes in Reporting
3.3 | UAT with Users
a | Provide, Test UAT User's Acces basis Security Profiles
b | Create UAT Test Cases
c | Test Reporting Reports
d | Show and Tell Reporting UI
4 | Sprint 2 - Phase 2 KPIs / Screens - Build & Deploy
4.1 | Data Modelling
a | Selection of Attributes, Columns & Matrix
b | Establish relationship between tables
c | Create Reporting Tables
4.2 | Reporting Build
a | Creation of Data Models in Reporting & Establish Relationships
b | Creation of Calculation & Major Matrix
c | Build Wireframes in Reporting
4.3 | UAT with Users
a | Provide, Test UAT User's Acces basis Security Profiles
b | Create UAT Test Cases
c | Test Reporting Reports
d | Show and Tell Reporting UI
7 | Sprint 3 - UAT and Sign-off - (ALL KPIs and Users)
7.1 | Provide access to key users with different security profiles to test
7.2 | Share UAT Test Scenarios
7.3 | Review and feedback from final users
7.4 | Fix data gaps identified during testing
7.5 | UAT Sign-off
8 | Go-Live
8.1 | Create user guides on how to use Reporting dashboards
8.2 | Orientation session with all end users
8.3 | Communication mail with User Guide
Formulas:
No of Days = IF(OR([Target Start Date]="",[Target End Date]=""),"",NETWORKDAYS([Target Start Date],[Target End Date])& " day(s)")